## Sheet1
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
Game Management | 70 | 40 | 2800 | 2023-04-20 |  | O | Gmae Management with win/lose scenarios is very important
Platform/Slider Physics | 70 | 40 | 2800 | 2023-04-14 |  | R | Implemented Slider physics and the platform physics Tasks + physics
Main Physics + Integrations | 70 | 70 | 4900 | 2023-03-23 |  | O | Another big ticket item
Satchel Physics | 3 | 8 | 24 | 2023-03-23 |  | O | Needs to get this resolved soon(info+eqs underway)
Display Hardware showing some issues | 70 | 100 | 7000 | 2023-04-20 |  | O | Display hardware is having some weird issues, need to fix this ASAP
Capstone Project | 70 | 40 | 2800 | 2023-04-07 |  | O | End stages of a huge Capstone Project delivery by 28th April
Using LCD to draw shapes and stuff | 13 | 20 | 260 | 2023-04-14 |  | M | Was able to accomplish this this week
Implement Rail Gun | 40 | 8 | 320 | 2023-04-07 |  | M | I implemented this
Implement LED | 40 | 13 | 520 | 2023-04-07 |  | O | Did'nt think much of it now but need to mitigate it soonish(End Item)

## Sheet2
Valid Modified Fibonacci values
1
2
3
5
8
13
20
40
70
100